Department Of Health

Quality Improvement Work Plan

Calendar Year

2013

Updated 1/29/2013

As part of the agency’s Quality Improvement Program, we identify opportunities to improve and enhance our services and performance through active planning and performance monitoring.  Quality improvement activities are identified throughout the department with the help of our employee suggestions, Health of Washington State, State Health Improvement Plan, and our agency strategic planning process.   The projects listed below are quality improvement projects in various implementation stages.

Projects completed in 2012

| Activity | Start Date | Project Leads | Date Completed | Comments |
| --- | --- | --- | --- | --- |
| Web Redesign | 2/2008 | Laura Blaske | 4/2012 | New web site launched |
| Drinking Water State Revolving Fund | 1/2012 | Kristin Betridge (Department of Health) and John LaRocque (Dept. of Commerce) | 8/2012 | On June 1st the Public Works Board approved the list of low risk loan recipients. Medium and high risk recipients were approved in August |

Projects carried forward

| Activity | Start Date | Project Leads | Date Completed | Strategy | Progress |
| --- | --- | --- | --- | --- | --- |
| Health Information Exchange | 1/2012 | David Jennings Co-lead TBD |  | Enhance our surveillance systems with data available through the Health Information Exchange. | Requested support for obtaining additional funding. Health Map presentation in November 2012 and a progress update is scheduled for 2013. |
| Public Health Reporting of Electronic Data | 1/2012 | Wayne Turnberg |  | Increase our capability to receive laboratory data through the Washington State Health Information Exchange into Public Health Reporting of Electronic Data system. | Significant work has been done to change PHRED to allow it to meet the Health Level 7 (HL7) standard for interoperability of health information technology. Health Map presentation scheduled for December 2012 and a progress update is scheduled for December 2013. |
| Integrated Infectious Disease Collection System | 1/2012 | Wayne Turnberg |  | Modernize our integrated infectious disease data collection system and to identify a sustainable funding source for system development and maintenance. | They are clarifying roles and responsibilities between the business programs and DIRM. Health Map presentation scheduled for December 2012 and a progress update is scheduled for December 2013. |
| Remove barriers and streamline regulatory processes | 1/2012 | Steve Saxe |  | Identify opportunities for revision to WACs to ensure our standards are consistent with advances in health care practice and technology, and rapidly changing patient care approaches and decrease the time to process a veteran application. | They have completed the draft cross-walk of the 22 military professions. Health Map presentation in August 2012 and a progress update is scheduled for August 2013. |
| Prescription Monitoring | 1/2012 | Steve Saxe |  | Improve systems that impact patient care by increasing the use of the prescriptive monitoring system. | A vendor was hired to produce video tutorials. Work should be completed in November 2012. Health Map presentation in August 2012 and a progress update is scheduled for August 2013. |
| On-line transactions | 1/2012 | Sam Marshall Don Peck |  | Deliver online renewal capacity for 185 license types and online new application capability for 8 license types by June 2013. | On July 16, 2012, four additional credential types were added for online renewal. Health Map presentation scheduled for Dec. 2012 and a progress update is scheduled for Dec. 2013. |
| Fiscal monitoring | 1/2012 | TBD |  | Modernize our fiscal monitoring system to ensure accountability for contracted funds. | A person was hired to act in a fiscal monitoring role for the 35 local health jurisdictions. Health Map presentation in Nov. 2012 and progress update is scheduled for Nov. 2013. |
| Workforce Development Plans | 1/2012 | J. Michelle Swope |  | Have a workforce development system that coordinates and promotes the growth and development of all employees. | A workforce development manager has been hired. Health Map presentation in Sept. 2012 and progress update is scheduled for Sept. 2013. |
| Leave Automation | 1/2012 | Elizabeth Smith |  | Create an electronic leave approval system | Leave automation system has been developed and will be pilot tested in December, 2012. Presentation to Quality Steering Committee October 2012. |

New projects for 2012 - 2013

| Activity | Start Date | Project Leads | Date Completed | Strategy | Progress |
| --- | --- | --- | --- | --- | --- |
| Hospital Surveys | 6/2012 | Trent Kelly |  | Increase the efficiency of the hospital licensing process to ensure surveys are completed within timelines. | Conducted a VSM event in June 2012. They evaluated the number of inspectors needed in relation to the size of the hospital and developed streamlined procedures for collecting information during an inspection. Health Map presentation in October 2012 and progress update scheduled for Sept. 2013. |
| Agency Contracts | 11/2012 | Diane Offord |  | Improve the process for contracting agency funds to reduce the amount of time from initiation to contract going out for signature. | VSM was conducted October 2012. The implementation plan is being finalized. Health Map presentation is scheduled for 4/2013. |
| Hiring process | TBD | Todd Bacon |  | Reduce the number of steps and design a standard transparent agency process to select the most qualified and diverse candidates in the least amount of time. | Training is scheduled for February 25, 2013. The VSM is scheduled for March 4 – 7, 2013. Health Map presentation is scheduled in July 2013 |
| UW Grants Management | TBD | Joint project with DOH, Ecology, DSHS, Commerce, and UW. |  | TBD. Scoping committee is meeting 1/22/13 | Pre-planning meeting is being coordinated through the Governor’s office in December. Value stream mapping event is scheduled for February 27 – March 1, 2013 |