## Slide 1
Department of Health
Early Intervention Program Lean Launch
March 25th – March 28th, 2013

## Slide 2: Launch Overview
  Review of Lean principles and concepts
  Mapped the Current State of the Process
  Identified Issues, Pain Points and Ideas for Improvement
  Revisited Goals
  Envisioned Future State
  Prioritized Issues, Pain Points and Ideas for Improvement
  Identified Kaizens (focused objectives)
  Discussed Next Steps following the Launch

## Slide 3: Launch Photos

## Slide 4: Launch Photos

## Slide 5: Team Photo

## Slide 6: Launch Team Charter

## Slide 7: Team’s Process Goals/Aim Statement
Create an efficient process for determining EIP client eligibility and subsequent enrollment into EHIP by April 1, 2014. To accomplish this we will:
EIP Role:
Begin successfully tracking applications received by two categories: mini and full by April 1, 2013.
Establish baseline of completed full applications by July 1, 2013.
Increase the percentage of completed mini applications from 80% to 85% by July 1, 2013 and to 95% by January 1, 2014.
Once baseline result has been established on completed full applications, a target will be determined.
Increase the percentage of EIP applications processed within 10 business days from 10% to 35% by July 1, 2013 and to 60% by January 1, 2014.
Increase the average number of EIP applications processed per week from 120 to 150 by July 1, 2013 and to 200 by April 1, 2014 or 100% of applications received if less than these totals.

## Slide 8: Team’s Process Goals/Aim Statement
EIP and EHIP Combined Roles
Decrease the staff time necessary at both EIP and EHIP to monitor data exchange from 40 hours per month to 10 hours per month by April 1, 2014.
Modify data sharing requirements and processes to reduce duplicative work between EIP and EHIP staff.
Eliminate the need for two separate client applications to EIP and EHIP by April 1, 2014.

## Slide 9: Customer’s Value Perspective
Understanding how income is defined
6 month renewals burdensome
Short form works well
Case manager and client communication
Information on letters and insurance card
Medical appointments
Pharmacy issues
Use of electronic methods to share and transfer information

## Slide 10: Current State Map - EIP

## Slide 11: Summary of the Current State Map

## Slide 12: Current State Map – EHIP

## Slide 13: Summary of the Current State Map

## Slide 14: Summary of the Current State Map

## Slide 15: Envision the Future State - EIP
Client completes an on-line data stream that comprises a client application
Review client information to determine eligibility
Approve or deny application

## Slide 16: Envision the Future State - EHIP
Receive application through EIP data exchange
Evaluate application
Ensure completeness
Process the application
Approve or deny insurance application

## Slide 17
Identified 58 ideas that connect to the 58 pain points
  Online - combined application
  Client access to check their eligibility
  Real time data exchange
  Eliminate paper waste
  Increased access to data portals
Ideas for Improvement

## Slide 18: Key Process Improvement Opportunities
We addressed all 58 issues--
  Identified where in the process they fell, and what problem it addressed
  Categorized them in “themes” and eliminated duplicates

## Slide 19: Kaizen (continuous improvement) Action Plan
      Kaizen 1: Customer Service
      Kaizen 2: Contract
      Kaizen 3: Staffing Resources
      Kaizen 4: Training
      Kaizen 5: Procedures/Systems
      Kaizen 6: Policies
      Kaizen 7: IT
      Kaizen 8: Communications/Web
      Kaizen 9: Reporting

## Slide 20: Lessons Learned (Day 1)

## Slide 21: Lessons Learned (Day 2)

## Slide 22: Lessons Learned (Day 3)

## Slide 23: Next Steps
Within two weeks
  Team is meeting weekly
  Kaizen Groups are completing actions weekly
  First visual board is up and being used
  Team meetings are held at the visual board
  Determine how to collect data (baseline)
30/60/90 day/Check-ins
  Team will step back (pause and look at the big picture), reflect and make any needed adjustments
  Provide an update to sponsors, key customers and process partners