PLAN

Identify an opportunity and

Plan for Improvement

1.  Getting Started

- Obesity identified as one of the top 4 health issues in the Lakes Region by Community Needs Assessment Survey 2008 respondents (41%) www.lrpph.org

- Belknap County: highest percentage of overweight and obese WIC enrolled children of all counties in NH (2007 CDC Pediatric Nutrition Surveillance System)

- 75.3% of Belknap County residents consume less than 5 servings  of fruits and vegetables a day (2007 NH BRFSS)

- Lakes Region Physical Activity and Nutrition Committee (PAN) active, but lacking resources

- Pleasant Street School enthusiastic about having coordinator to facilitate their ideas

- NO Access to student BMI at Pleasant Street School

- Difficulty establishing AIM

2.  Assemble the Team

- SAU 30 Superintendent – Bob Champlin - sparkplug

- Pleasant Street School Staff including: Charles Dodson, Principal; Marie Liimatainen, Nurse; Darlene Page, Second Grade Teacher; Sonja Roberts, Fifth Grade, Tim Goosens, SAU Food Director, Anne Barach, Guidance Counselor and members of the PAN Committee: LRGHealthcare (Dieticians, Education and Outreach), Parks and Recreation Director, UNH Extension Specialist, Belknap-Merrimack CAP and Laconia Child Care Director

3.  Examine the Current Approach

- School had high level of interest but fragmented coordination

- Nurse and Guidance Counselor teach a 4 week wellness curriculum for 5th grade

- Few activities related to healthy eating/active living

- Goal before MLC-3 was to remove Chocolate Pop Tarts from cafeteria

- Susan Laverack coordinated PAN and Pleasant Street School Staff (QuILT)

4.  Identify Potential Solutions

- Enthusiasm and interventions suggested based on 5-2-1-0

- Conclusion: 5-2-1-0 as primary intervention with a focus on the “5” in one Second Grade

- Consulted with nutritional experts at DHHS and local level

- Determined all possible ways food is consumed by students before, during and after school- greatest potential to impact improvement at snack time.

5.  Develop an Improvement Theory

Through multi-component nutritional intervention including nutritional education, taste testing, encouragement and positive reinforcement, the percentage of 2nd grade students who bring a fruit or vegetable for snack will increase.

Aim: Second Grade Students will bring fruit and/or vegetable for snack at least 60% of the time by June, 2009

DO

Test the Theory for Improvement

6.  Test the Theory

- Multi-component nutritional information to 2nd grade students

- Taste Testing at snack time

- MLC grant $$ to purchase F&V and donations of healthy foods

- Visit to grocery store

- “Book Buddies” with 5th Grade

- Design of bulletin board

- Integrate project into school’s Wellness Committee

- Integrate F & V across the curriculum

- Spring, 2009 – School-Wide Challenge: class to bring most fruits and vegetables for snack in a week’s time – Principal’s Tie Award-This may help jumpstart 2nd grade levels that dropped in Feb.

STUDY

Use Data to Study Results

of the Test

7.  Check the Results

- Pre-Post test results (Nov. 2008-Jan 2009)  of 2nd-graders’ revealed increased knowledge in identification and nutritional benefits of fruits and vegetables

- We discovered that with the taste testing and grant to provide healthy snacks, the numbers of students eating healthy foods increased, even if they were not actually bringing the snacks themselves.

- The numbers of students bringing or consuming fruits or vegetables to school for snacks increased to 77% by the end of the school year, surpassing our goal.

ACT

Standardize the Improvement and Establish Future Plans

8.  Standardize Improvement

or  Develop New Theory

- Revisit AIM statement

- 5th Grade to “pilot” F&V at snack time

- Second Grade to sustain and increase F&V consumption at snack time

9.  Establish Future Plans

- Improve processes for working with QuILT members

- Broaden successes to 5th grade – developmentally-appropriate activities (e.g., student involvement in tracking tools and data collection)

- Utilize potential HEAL funding source to spread to other schools within region

- Explore Snack Policy (informal): create school-wide practice “this is how we do it” relating to Fruits and/or Vegetables

- Pursue funding for “Organ Wise Guys”

# Text boxes

67 Water Street, Laconia, NH  03246  (603) 528-2145

Pleasant Street School 5-2-1-0 – Fruits and Vegetables for School Snack Time

Quality Improvement Story Board

This work was funded

by the Robert Wood Johnson Foundation

Multistate Learning Collaborative -3 Grant # 64188