## Sheet1
Master Action Planner
| Action Activities | Start Date | Completion Date | Materials and Resources Needed | Responsibility | Strategy | Completed
1 | Conduct CHAT Core Measures Subcommittee Meeting (s) to: Review existing assessment tools, combine/revise questions and develop 1st draft of core measure assessment tool. | June, 2012 | September, 2012 | All existing tools from ADHS programs including existing Health Start and HRPP home assessment forms. | Cristina Ochoa, Dianne Eckles, Sara Rumann, Tifney Tihey | #1 Core Items | X
2 | Draft 1 of Core Measures Assessment Tool presented to CHAT for review. Comments and changes obtained, name for tool is decided: "Healthy @ Home" Arizona Home Safety and Family Wellness Assessment. |  | August, 2012 | Draft 1 of Core Measures | Cristina Ochoa, Dianne Eckles, Sara Rumann, Tifney Tihey | #1 Core Items | X
3 | Draft is revised for further review and Draft 2 is sent to Tomi St. Mars, Injury Prevention for comments/changes. |  | 2012-08-16 | Draft 2 of Core Measures | Cristina Ochoa | #1 Core Items | X
4 | Draft 3 (with Tomi's edits) is sent to Health Start and NICP Contractors for review and comment. Survey Monkey is developed for their responses. | 2012-08-16 | 2012-08-23 | Draft 3 of Core Measures | Tomi St. Mars, Cristina Ochoa | #1 Core Items | X
5 | Draft 3 is presented to Injury Prevention Advisory Council for review and comment |  | 2012-08-29 | Draft 3 of Core Measures | Cristina Ochoa, Sara Rumann | #1 Core Items | X
6 | CHAT Subcommittee on Core Measures convenes to discuss suggestions and changes (IPAC and contractors) |  | 2012-08-29 | Comments and suggested changes from Contractors and IPAC team | Sara Rumann, Cristina Ochoa | #1 Core Items | X
7 | Complete final draft 4 of Healthy @ Home Assessment Tool |  | 2012-08-29 |  | Cristina Ochoa, Dianne Eckles, Sara Rumann, Tifney Tihey | #1 Core Items | X
8 | Present Draft 4 to CHAT for final review and comment |  | 2012-09-10 | Draft 4 of Core Measures | Cristina Ochoa | #1 Core Items | X
9 | Revise Healthy @ Home Assessment Tool as needed, complete FINAL Draft 5. |  | 2012-09-10 | Draft 4 of Core Measures | CHAT Team, Cristina Ochoa | #1 Core Items | X
10 | Translate Healthy @ Home Assessment Draft 5 into Spanish |  | September, 2012 | Draft 5 – English and Spanish | Cristina Ochoa | #1 Core Items | X
11 | Collect education and referral material from AZ Living Well Institute, Environmental Health (Lead and asthma triggers) and home safety issues. |  | October, 2012 | New Hampshire Assessment Form example | Diane, Jessie, Sara, Toni, MaryEllen, Tim, Injury Prevention, Cristina Ochoa | All Action Committees | X
12 | Create the Referral and Education check list and accompanying information sheets for home safety, environmental health and chronic disease that is attached to the Health @ Home Assessment Form |  | October, 2012 | Education and referral material collected. | Cristina Ochoa, Sara Rumann, Tim Vaske, Toni Means | All Action Committees | X
13 | Review current HSP and NICP Policy and Procedure Manual sections that address the use of home assessments including the Safe Home/Safe Child form |  | September, 2012 (Oct 3 & Oct 17) | Review current Policy & Procedures sections and other examples. | Sara Rumann, Cristina Ochoa, Valerie Odeh | #2 Policies & Procedures | X
14 | Action Commitee #3 "Training" to create and send Policy & Procedure information regarding training to Action Committee #2. |  | October, 2012 | Review current Policy & Procedures sections and other examples. | Diane Eckles, Jessie Toperek, Cristina Ochoa | #3 Training | X
15 | Action Commitee #4 "Data Collection" to create and send Policy & Procedure information regarding data collection, referrals and reporting to Action Committee #2. |  | October, 2012 | Review current Policy & Procedures sections and other examples. | Tim Vaske, MaryEllen Cunningham, Cristina Ochoa | #4 Data Collection | X
16 | Action Commitee #5 "Pilot" to create and send Policy & Procedure information regarding implementation and administration of assessment tool to Action Committee #2. |  | October, 2012 | Review current Policy & Procedures sections and other examples. | Sara Rumann, Mary Ellen Cunningham, Cristina Ochoa | #5 Pilot | X
17 | Identify the Policy and Procedure criteria and detailed steps under each of the following sections collected from all action committees: Administration, Training, Data Collection, Reporting |  | October, 2012 | Information collected from action committees. | Toni Means, Tifney Tihey, Sara Rumann, Cristina Ochoa | #2 Policies & Procedures | X
18 | Complete a list of barriers that may occur to implementing new Policy and map out soultions |  | October, 2012 |  | Toni Means, Tifney Tihey, Sara Rumann, Cristina Ochoa | #2 Policies & Procedures | X
19 | Create a first draft of Policy and Procedures for the Healthy @ Home Assessment |  | October, 2012 |  | Sara Rumann, Valerie Odeh, Tifney Tihey, Toni Means, Cristina Ochoa | #2 Policies & Procedures | X
20 | Present Draft 1 of Policies and Procedures to CHAT |  | 2012-10-22 | Draft 1 of P&P | CHAT Team | #2 Policies & Procedures | X
21 | Send out Draft 1 of Policies and Procedures for review by HSP and NICP contractors | 2012-12-03 | 2012-12-10 | Draft 1 of P&P | Sara Rumann, Valerie Odeh | #2 Policies & Procedures | X
22 | Review comments from CHAT and Contractors on Policy and Procedures and revise Draft 1 as needed | 2012-11-01 | December, 2012 | Input and comments from contractors and CHAT | Cristina Ochoa, Subcommittee and CHAT | #2 Policies & Procedures
23 | Create an Executive Summary |  | November, 2012 |  | Toni Means, Tifney Tihey, Sara Rumann, Cristina | #2 Policies & Procedures
24 | Create an FAQ list for home visitors |  | November, 2012 |  | Toni Means, Tifney Tihey, Sara Rumann, Cristina Ochoa | #2 Policies & Procedures | X
25 | Finalize the new Policy & Procedures for H@H |  | December, 2012 | Draft 2 of the P & P | Toni Means, Tifney Tihey, Sara Rumann, Cristina | #2 Policies & Procedures | X
26 | Revise policy and procedures based on feedback from pilot sites after 3-4 months as needed. |  | June, 2012 | Final Draft of the P & P | Sara Rumann, Valerie Odeh | #2 Policies & Procedures
27 | Integrate new policy into the existing Policy and Procedures Manuals for HSP and NICP. |  | August, 2012 |  | ADHS | #2 Policies & Procedures
28 | Determine method of training home visitors. Training will be conducted via powerpoint webinar (9/10) |  | September, 2012 |  | Diane Eckles, Jessie Toperek, Sara Rumann, Cristina Ochoa | #3 Training | X
29 | Action Commitee #2 "Policy and Procedures" to create and send training information regarding policies and procedures to Action Committee #3. |  | 2012-11-01 |  | Sara Rumann,Toni Means, Tifney Tihey, Cristina Ochoa, Valerie Odeh | #2 Policies & Procedures | X
30 | Action Commitee #4 "Data Collection" to create and send training information regarding data collection, referrals and reporting to Action Committee #3. |  | 2012-11-01 |  | Tim Vaske, MaryEllen Cunningham, Cristina Ochoa | #4 Data Collection | X
31 | Action Commitee #5 "Pilot" to create and send training information regarding implementation and administration of assessment tool to Action Committee #3. |  | 2012-11-01 |  | Sara Rumann, Mary Ellen Cunningham, Cristina Ochoa | #5 Pilot | X
32 | Collect information relevant for training of pilot sites from Chronic Disease, Environmental Health and Bureau of Women's and Children's Healh. |  | 2012-11-15 |  | Diane, Jessie, Sara, Toni, MaryEllen, Tim, Injury Prevention, Cristina Ochoa | #3 Training | X
33 | Develop a H@H training PowerPoint presentation for pilot sites with modules for chronic disease, environmental health, administration of H@H assessment, Data collection, reporting and policies and procedures. | September, 2012 | December, 2012 | Healthy@Home Assessment, PowerPoint software, education material from EH, CDSM and home safety sections. | Diane Eckles, Jessie Toperek, Cristina Ochoa | #3 Training | X
34 | Coordinate training dates and schedule training for all home visitors in pilot sites. | December, 2012 | January, 2012 | Scheduling software/website | Cristina Ochoa, Sara Rumann, Valerie Odeh | #3 Training | X
35 | Provide training to pilot site home visitors through Webinars |  | January, 2012 | Training Modules. Possibly I-linc, Siren bridge, or conference room. | Cristina, Diane, Jessie, Sara, Valerie | #3 Training
36 | Revise training material for expansion of the assessment tool use to all HSP and NICP sites |  | 2013-06-01 |  | CHAT Team | #3 Training
37 | Verify resources and start-up costs for data entry process |  | November, 2012 | Existing resources | Mary Ellen Cunningham | #4 Data Collection | X
38 | Identify obstacles to data collection by meeting with home visitors for input and map out solutions. |  | October, 2012 |  | Mary Ellen Cunningham, Tim Vaske, Sara Rumann | #4 Data Collection | X
39 | Determine method of data entry: scan-able, manual input. |  | November, 2012 |  | Mary Ellen Cunningham, Tim Vaske, Sara Rumann, Cristina Ochoa | #4 Data Collection | X
40 | Develop database for data entry | 2012-10-10 | November, 2012 |  | Cristina Ochoa, Sara Henry | #4 Data Collection
41 | Train and coordinate data managers. |  | December, 2012 |  | Mary Ellen Cunningham, Tim Vaske, Sara Rumann, Cristina Ochoa | #4 Data Collection
42 | Determine system of tracking enrollment/completion in CDSM programs. |  | November, 2012 |  | Tim Vaske | #4 Data Collection | X
43 | Coordinate with AZ Living Well Institute to provide de-identified reported referrals from AZDHS home visiting programs. |  | November, 2012 |  | Tim Vaske | #4 Data Collection | X
44 | Finalize data collection process. |  | December, 2012 |  | Mary Ellen Cunningham, Tim Vaske, Sara Rumann, Cristina Ochoa | #4 Data Collection | X
45 | Collect data including assessment form and referral and education checklist monthly from pilot sites through billing |  | February, 2013 |  | Sara Rumann, Valerie Odeh | #4 Data Collection
46 | Input data using determined method of entry. |  | April, 2013 | Materials and resources needed for data entry | ADHS | #4 Data Collection
47 | Report back to home visiting programs on referrals and assessment tool findings. |  | April, 2013 |  | Sara Ruman, Tim Vaske, Mary Ellen Cunningham, Cristina Ochoa | #4 Data Collection
48 | Once more HSP and NICP sites use the new assessment tool, revise data collection and data entry process and implement |  | July, 2013 |  | CHAT Team | #4 Data Collection
49 | Identify three HSP and two NICP site to be the pilot sites for the H@H Assessment Tool |  | 2012-11-12 | List of Contractors and contacts and sites that volunteer for pilot | Sara Rumann, Valerie Odeh | #5 Pilot | X
50 | Distribute Final Policies and Procedures to pilot sites |  | November, 2012 | Revised Policy & Procedures forms | Cristina Ochoa, Sara Rumann, Valerie Odeh | #5 Pilot | X
51 | Ensure training for pilot sites has been completed |  | January, 2013 |  | Sara Rumann, Valerie Odeh | #5 Pilot
52 | Launch the Implementation of the new Assessment Tool by distributing H@H assessment and materials to pilot sites. |  | February, 2013 |  | Sara Rumann, Valerie Odeh, Mary Ellen Cunningham | #5 Pilot
53 | Obtain feedback from the Pilot sites on the assessment and referral process and revise policy and procedures, data collection and forms as needed |  | April, 2013 |  | Sara Rumann, Valerie Odeh, Mary Ellen Cunningham | #5 Pilot
54 | Implement the revised process in all the HSP and NICP Programs |  | July, 2013 |  | Mary Ellen Cunningham, Valerie Odeh | #5 Pilot
55 | Share the H@H assessment tool and other information learned with the IPAC and other Home Visiting Programs |  | July, 2013 |  | CHAT Team | #5 Pilot