## Nov 30
QI Project: Process and Database Status Report Check 11/30/2012
By November 30, 2012
Task |  |  | % Complete |  |  |  | Performance Improvement Measures | [5 empty] | numerator | denom | rate
AIM Statement |  |  |  | 100 |  |  | Targeted databases (n=3)
Improvement Process Map |  |  |  | 100 |  |  | Targeted database changes made | [5 empty] | 2 | 3 | 0.66667
Initial data collection for planning phase |  |  |  | 100 |  |  | Quality assurance checks of targeted dbs | [5 empty] | 1 | 3 | 0.33333
Plan to measure customer satisfaction with the process |  |  |  | 100 |  |  | Fully compliant targeted databases | [5 empty] | 1 | 3 | 0.33333
Measure of satisfaction with the process |  |  |  | 100 |  |  | Compliant by 11/30/2012 | [5 empty] | 1 | 3 | 0.33333
Written plan to achieve compliance for identified databases |  |  |  | 100 |  |  | CQI: Expect Compliance by 1/1/2013 | [5 empty] | 2 | 3 | 0.66667
Recommendations for continuous quality improvement |  |  |  | 100 |  |  | Other 5 selected databases (Electronic and paper worksheets broken out separately)
[7 empty] | Database changes made | [5 empty] | 3 | 7 | 0.42857
[7 empty] | Quality assurance checks of dbs | [5 empty] | 3 | 7 | 0.42857
[7 empty] | Fully compliant databases | [5 empty] | 3 | 7 | 0.42857
[7 empty] | Compliant by 11/30/2012 | [5 empty] | 3 | 7 | 0.42857
[7 empty] | CQI: Expect Compliance by 1/1/2013 | [5 empty] | 5 | 7 | 0.71429
Improvement Process Check List
|  | Review 2007 and 2010 Surveys | Cross-check against selection criteria | Met with DB Owner/ Mgr | Type of issues to fix in EDB* | Requested cost/time estimates to fix EDB | Is fix to EDB feasible? | Formal plan in place to fix EDB | Fixed EDB; QA check | Fully compliant EDB | Type of issues to fix in paper form(s) | Requested cost/time to fix paper form(s) | Is fix to paper form(s) feasible? | Formal plan in place to fix paper form(s) | Fixed paper form(s); QA check | Fully compliant paper form(s) | Comments
Major Databases Targeted for Improvement
| Birth Registry | Y | Y | 2012-06-26 | NA | NA | NA | NA | NA | NA | G, E (BC worksheets) | 2012-07-24 | Y | 2012-08-06 | 2012-11-28 | 2012-11-28 | Electronic birth registry will be updated in 2014; Medical worksheet and 2 birth certificate parent worksheets need revisions and translation into Spanish
| CT Immunization Registry and Tracking System (CIRTS) | Y | Y | 2012-06-12 | G, R | N | N | N | NA | NA | NA | NA | NA | NA | NA | NA | Most of data is fed from Birth registry; "other" gender and open text field needed; modify option to select multiple races of mother
| Health Practitioner Licensure (eLicense) | Y | Y | 2012-06-07 | NA | NA | NA | NA | NA | NA | G, E, R | 2012-08-13 | Y | 2012-08-13 |  |  | Need approval from other state agencies and programs; scope of project is make changes to paper forms; vendor costs/time for EDB changes (outside of scope); race and ethnicity not broken out separately; cannot multi-select for race; As of 11/30/12 - form updates are 95% done
Other Databases Meeting Criteria for Improvement
| Adult Blood Lead Epidemiology and Surveillance (ABLES) | Y | Y | 2012-06-04 | G | Y | Y | Y | 2012-11-27 | Y | NA | NA | NA | NA | NA | NA | Lab reports come from may different sources; need "other" gender category with open text field in electronic database (Maven)
| CT Influenza Surveillance: Now part of CT EDSS | Y | Y | 2012-06-12 | G | 2012-06-12 | Y | 2012-07-26 | 2012-11-27 | Y | G, E (OL-15c) | 2012-07-31 | Y | Y |  |  | Modify OL-15c and PD-23 forms; sent change request to steering committee; changes to paper forms expected 1/1/13; EDB can be changed by 11/30/12, a statement of work to the vendor has been submitted
| Tuberculosis Program (formerly TIMS) | Y | Y | N | [12 empty] | Program staff not able to work on this project at this time due to lack of time and resources
| Occupational Injury and Illness Surveillance | Y | Y | 2012-06-04 | G | Y | Y | Y | 2012-11-27 | Y | G | Y |  |  |  |  | Need approval from Dept. of Labor who owns the form and also uses it; plan to meet to discuss with Labor this winter (2012-2013)
| Surveillance Epidemiology and End Results (SEER) Data Management System | Y | Y | 2012-06-12 | G | 2012-06-12 | Y | Y |  |  | NA | NA | NA | NA | NA | NA | Local change to database can be doneby 12/12/12. Will cost $0 and DPH IT can make change.
*Abbreviations
EDB = electronic database
NA = Not applicable
G=gender, R=race, E=ethnicity, A=age
Notes:
1. The number of databases able to be revised, either EDB or paper report, depends on if they meet criteria for selection.