## GANTT Chart
GANTT CHART
Goals & Strategies | Whose Responsibility | may | jun | jul | aug | sept | oct | nov | dec | Tools needed | Progress | Output | Outcome | Staff Roles
Goal: establish responsibility and ownership of the influenza administration program through defined roles & protocols | [13 empty] | Primary Nurse: Jeni
determine what training you need from IDPH for IRIS | AIDEP team | [8 empty] | list of items- Bethany | done- via email |  | Have a competent team approach that ensures timely IRIS data entry. | Secondary Nurse: Bethany | bar: jun
request IRIS training | Bethany | [9 empty] | done- emailed IRIS |  |  | Primary Admin. Aide: Sandy | bar: may
take IRIS training | AIDEP team | [9 empty] | completed July 18, 2017 | training attendance log, done |  | Secondary Admin. Aide: | bar: jul
obtain updated list from Patti for accepted insurance & provide to all involved staff prior to flu season (Bethany, Val, Diane, Jeni, Jodi, Betty) | Sandy/Bethany | [8 empty] | insurance list | Patti updated list- 7/25/17 and 9/2017 to include Aetna high deductible plan | insurance list distributed, need to get copies to 5 additional staff |  | Primary Float: | bar: aug
For Outreach Clinics | [9 empty] | process flow for outreach- Jeni | bar: aug
review existing layouts for clinic set-up | All AIDEP staff/Bethany | [9 empty] | Discussed check in process flow, AA to front of room, nurses in back, table signs with numbers | bar: may to dec
create and print a standardized cover sheet that the lead nurse will fill out for each clinic | Sandy/Jeni | [9 empty] | Need to update form to include staff who have forms | bar: may to dec
check with Family & Community Health Manager for incoming BSN students | Jeni | [9 empty] | Not at this time. | bar: may to dec
check with schools to determine if there are volunteers to help staff large clinics | Jeni | [9 empty] | Not at this time. | bar: may to dec
instruct billing staff on what they can expect prior to season | Jeni | [9 empty] | distribute flu pricing sheet and receipt | bar: may to dec
create hanging folder with tabs that identify each outreach clinic | Sandy | [9 empty] | done-in bottom drawer of file cabinet in Sandy's office behind desk | bar: may to dec
create instruction sheet | Jeni | [8 empty] | process flow for outreach- Jeni | update from 8/3/17 meeting | bar: may to dec
coordinate outreach clinics | Jeni | [9 empty] | started, spreadsheet in progress | bar: may to dec
practice mass vaccination dispensing clinic if expecting over 100 - use guideropes | All?- Jodi | [9 empty] | Not at this time. Improve flow- register here sign? | bar: may to dec
schedule Sandy to attend all outreach clinics, if applicable | Jeni | [9 empty] | In progress 8/3/17, Done | clinic schedule | bar: aug to oct
schedule data entry time on the end of outreach clinics for all staff involved | Jeni | [9 empty] | In progress 8/3/17, Done | bar: aug to nov
create and send outreach clinic schedule to all involved staff | Jeni | [9 empty] | In progress 8/3/17, Jeni will send meeting invitations for outreach clinics assigned | bar: may to dec
ensure all staff have internet access through transportable computers | Jeni | [9 empty] | Sandy added on list for Surface, Jeni to check hot spot use with Ryan, DONE | bar: aug
ensure there is a laptop/surface dedicated to outreach clinics with a number key pad | Jeni | [9 empty] | 9/2017 No number key pad at office per Ryan. All staff have Surface access. | capable computer | bar: aug
prepare outreach totes: vaccine and supply | Jeni | [8 empty] | checklist & "ready" sign- Jeni | Done 9/2017 | fully stocked totes (tally on wall of how many times "not ready") | bar: sept to dec
prepare ALL outreach totes: paperwork, scanner & money bag & place "ready" sign on totes | Sandy | [9 empty] | Forms: consents, VIS (flu, both pneumococcal), receipts, insurance cheat sheets, price list, | bar: sept to dec
check clients in to outreach clinic | Lead AA | bar: sept to dec
verify date of birth and insurance written on form by reading birthdate back to client | Lead AA | bar: sept to dec
highlight date of birth | Lead AA | [8 empty] | protocol for check-in- Sandy | protocol for checkin completed, 10/2017 not doing the highlighting | 0 incorrect DOBs when filing | bar: sept to dec
ensure all participant forms are filled out correctly onsite | Lead AA | [9 empty] | 10/2017 Continue to make sure no missing documentation on flu consent forms. | bar: may to dec
follow protocol for administering immunizations at outreach | RNs working the clinic | bar: sept to dec
at each clinic, ensure money bag, all forms & flash drive are accounted for | Lead AA | bar: may to dec
complete IRIS data entry on site if less than 20 shots given, if possible | Lead Outreach Nurse & AA | [9 empty] | 8/3/2017 Diane to return flash drive to Sandy once completed 10/17/17 Not doing the flash drives, Data entry at the majority of outreach clinics done excluding school based | bar: sept to dec
fill out cover sheet at end of each clinic and attach to clinic forms. | Sandy/Lead RN | [9 empty] | 10/17 not consistently done | bar: may to dec
return from clinic, make copies of all consent forms. | Sandy/Lead RN | bar: may to dec
Give copied consent forms and properly labeled envelope of cash & properly labeled flash drive to Diane - not using flash drive, using work cell phones or surface | Sandy | [9 empty] | Diane is printing off copies of insurance cards from R: drive after being uploaded by work phone | bar: may to dec
count consent forms and split evenly among staff who were at clinic | Sandy | bar: may to dec
restock outreach totes and put away vaccines | Lead Outreach Nurse | [9 empty] | 10/2017 No issues | bar: sept to dec
place completed cover sheet in each clinic hanging file | Sandy | bar: may to dec
enter original forms into IRIS within 7 days | All staff | [9 empty] | 10/17- all outreaches were completed. PHN patients were the only process not meeting this goal. | bar: may to dec
upon completion of data entry, place in hanging files according to outreach clinic location | All staff | bar: may to dec
fill out remainder of cover sheet, the number of forms in IRIS | All staff | bar: may to dec
five days after each outreach clinic, check IRIS to ensure forms are complete | Jeni | bar: may to dec
Enter completion data into shared outreach spreadsheet | Jeni | bar: may to dec
Determine if data entry is complete; if it isn't request help ask Jodi to send email to all staff | Jeni | bar: may to dec
Check outreach spreadsheet weekly to monitor for completion of IRIS data entry. | Jodi | [9 empty] | Spreadsheet created | 75% of data entry completed within 7 days | bar: may to dec
Update QI Superbill flowchart and disseminate with all parties involved | Bethany | [9 empty] | Bethany to meet with Marcy. Done 9/2017. | bar: aug
Determine cash bag flow | Jodi | [9 empty] | Keep bag in folder locked up at Sandy's desk, top draw on right side file cabinet | bar: aug
Add date and child's age on School/Childcare based forms, fix insurance section to be clear on 1 page (Newman and Tugs) | Bethany | [9 empty] | update for 18-19 | bar: nov
In Immunization Clinic
provide refresher training on flow for superbill | Jodi | [9 empty] | Emailed front console staff, completed | training attendance log | bar: aug
follow standard flow sheet for superbill at immunization check in | Diane/Bethany | [8 empty] | updated process QI flow- Jodi | sticky note $ on Superbill who need to pay for influenza vaccine? Have patient return superbill to front console with cost for vaccine to pay. | bar: aug to dec
follow protocol for administering immunizations in the clinic | RNs working the clinic | bar: aug to dec
each nurse determines if they will be able to enter immunizations (flu & pneumonia) into IRIS within 7 days; nurse covering clinic will enter their own | RNs working the clinic | bar: aug to dec
overflow data entry complete | first Sandy; second Betty | [9 empty] | 10/17 Not needed to ask for back up for the clinic yet. | bar: aug to dec
on Friday afternoons assign a back up nurse in the building to call if clinic gets backed up | Jodi | [9 empty] | Bethany meet with Sam for clinic. Jodi reveiwed flu schedule & calendar. Betty to back-up clinic on Sept. 29th, all other Friday's Jeni will be in the office to back up. | Betty scheduled to cover Sept. 29th. Jeni back-up all other Fridays. | bar: sept to oct
PH Nurses:
train PH Nurses on protocol for vaccine administration and IRIS data entry process | Bethany | [9 empty] | Contacted Val 7/29/2017 via email, met with nurses | bar: sept
prepare consent forms so there are enough and they are ready prior to flu season | Sandy | [9 empty] | VIS forms are the same | bar: aug
Update Superbill forms | Bethany | [9 empty] | Contacted Patti, updated 7/27/17 | bar: aug
follow protocol for administering immunizations to home bound patients | PH Nurses | bar: sept to dec
return all patient paperwork to bin within 2 days of immunization administration | PH Nurses | [10 empty] | percent of paperwork returned to bin in 2 days | bar: sept to dec
gather paperwork daily and enter into IRIS | Sandy | [9 empty] | Bethany: Talk with Val where they want the forms turned in for us to daily pick up, oriented Sandy to the process and Marcy updated flow chart and Jodi sent to all applicable staff | bar: sept to dec
turn in daily copies of the consent forms (buff paper) to Diane for billing | Sandy | bar: sept to dec
ADMINISTRATIVE
evaluate | Bethany | [9 empty] | PHN process not working, neet to determine why
how action plan is working: are people overwhelmed, are people feeling this is unfair, is someone doing the majority of the work? | Bethany | bar: sept to dec
evaluate achieving aim | Bethany | [9 empty] | 10/2017- reviewed and updated spreadsheet, updated team 10/19 | bar: oct; dec
JAIL
Send FluLaval vaccine to jail. | Jodi/Bethany | [9 empty] | Done 9/2017 | bar: sept
Receive flu consents back from Jail nurse.